## RAID Log
RAID LOG
Risks · Assumptions · Issues · Dependencies — template by Ritika Raje
ID | Type | Title | Description | Date Raised | Raised By | Impact | Likelihood | Priority | Owner | Response / Mitigation | Status | Due Date | Date Closed
R-01 | Risk | Key vendor may miss integration deadline | Vendor has flagged resourcing constraints that could delay the API integration milestone. | 2025-01-15 | R. Raje | High | Medium | High | Delivery Lead | Weekly checkpoint with vendor PM; identify fallback contractor by month-end. | Open | 2025-02-28 |  | ← example row, overwrite or delete

## How to use
HOW TO USE THIS RAID LOG
What it's for | A single, living record of the four things that quietly derail delivery: Risks (might happen), Assumptions (taken as true, unverified), Issues (already happening), and Dependencies (you're waiting on someone else).
Type | Pick Risk, Assumption, Issue, or Dependency from the dropdown. One item per row.
Impact / Likelihood | How bad if it lands, and how probable. Likelihood applies mainly to Risks.
Priority | Your call on urgency — Critical / High / Medium / Low. The row colours itself.
Owner | One named person. 'The team' owns nothing.
Response / Mitigation | The actual next move — not a description of the problem again.
Status | Open → In Progress → Closed. On Hold if genuinely parked.
Keeping it alive | Review at every delivery checkpoint. A RAID log nobody opens is just decoration — the value is in the weekly pass, closing what's done and re-scoring what's changed.
Editing | Row 4 on the log is an example — overwrite or delete it. Add rows as needed; dropdowns and colour rules cover rows 4–60.
ritikaaru.github.io/ritika.raje